## Sheet1
Formulea one |  |  |  |  | Formulea 2
old average + New average |  |  |  |  | sum of all prices/sum of all unit
|  | 10.5 |  | 0
price | unit | average price |  |  | price | unit | average price
100 | 10 | 10 | 10 |  | 100 | 10 | 10
110 | 10 | 11 | 10.5 |  | 110 | 10 | 10.5
100 | 10 | 10 | 10.25 |  | 100 | 10 | 10.3333

## cart design
cart id | user id | status | item | quantity
user cart
cart id | user id | status
InProgress / Comfired / Cancel
cart Details
cart Detail id | cart id | item | quantity | Status
Add /Remove
user orders | user cart
order id | cart id

## Reported Issues
No. | Description | Status | Column1 | Column2 | date
1 | if pressing enter on sale invoice item system is not responding | Done | Delivery 1
2 | name field of the items visible should be adjusted | Done | Delivery 1
3 | edit quantity in the sale invoice | Done | Delivery 1
4 | add address in the pdf invoice printing for the customer. | Done | Delivery 1
5 | brand image is not showing. | Done | Delivery 1
6 | Item giving error while entring from the web | Done | Delivery 1
7 | Sale Invoice show be able to edit. | Done | Delivery 1
8 | Delete Sale Invoice. | Done | Delivery 1
9 | Edit / Detete Sale Invoice. | Done | Delivery 1
10 | Remove row from the sale Invoice while edit sale. | Done need to be tested | Delivery 2
11 | update Quantity while making invoice. | Done need to be tested | Delivery 2
12 | Search in the stock Report Screen. | Done need to be tested | Delivery 2
13 | Sale Report should show the name of the customer. | Done need to be tested | Delivery 2
14 | Sale Return should show Quantity instead of Invoice to return an item. | Done need to be tested | Delivery 2
15 | Add Quantity in the sale report |  | Delivery 3
16 | Edit / Delete Purcahse Invoice. | Done need to be tested | Delivery 4
17 | Enter id for the stock report | Done need to be tested | Delivery 4
18 | search item in and add filter options | Done need to be tested | Delivery 4
19 | Issues fixed in Return stock | Done need to be tested | Delivery 5
20 | Purchse report / Edit purchase should have name of the supplier | Done need to be tested | Delivery 5
21 | Fixed the Edit purchase issue with the DB update | Done need to be tested | Delivery 5 |  | 2022-02-02
20 | Issues fixed in Return stock (complete logic change) | Done need to be tested | Delivery 6 | only gui cahnges | 2022-02-08
21 | refresh after the submit in the return sale | Done need to be tested | Delivery 7 | Both GUI / MW | 2022-02-16
22 | add name in the AR /AP instead of customer id | Done need to be tested | Delivery 7 | Both GUI / MW | 2022-02-16
23 | refresh after the submit in the AR / AP | Done need to be tested | Delivery 7 | Both GUI / MW | 2022-02-16
24 | in return if the the value goes to zero remove it from the sale details | Done need to be tested | Delivery 7 | Both GUI / MW | 2022-02-16
25 | Export to excel functionality in the Stock report. | Done need to be tested | Delivery 8 | Only GUI | 2022-03-17
26 | print name on every page of the sale invoice report | Done need to be tested | Delivery 8 | Only GUI | 2022-03-17
27 | add sum of all items on the stock report | Done need to be tested | Delivery 8 | Only GUI | 2022-03-17
28 | add sum in the AP /AR screen | Done need to be tested | Delivery 8 | Only GUI | 2022-03-17
29 | remove 0 entries from the AP/AR screen from details section | Done need to be tested | Delivery 8 | Only GUI | 2022-03-17
30 | Sale / Purchase history in stock report |  | Delivery 9 | Both GUI / MW | 2022-03-19
31 | show profit in the sale invoice detail |  | Delivery 10 |  | 2022-04-02
32 | in sale report if sale is less than cost then highlight the row |  | Delivery 10 |  | 2022-04-02
33
Edit / Delete expense sheet
show only online item having quantity greater than 0
timeout on huge purchase is causing issue
change the customer name in the sale invoice
if logged out subscriber should be redirected to login page
check how to add jwt password expiry retry
check item name is not getting updated
show customer last price when selecting the item
add summary like stock report on sale report
print purchase invoice