## Sheet1
Formulea one |  |  |  |  | Formulea 2
old average + New average |  |  |  |  | sum of all prices/sum of all unit
|  | 10.5 |  | 0
price | unit | average price |  |  | price | unit | average price
100 | 10 | 10 | 10 |  | 100 | 10 | 10
110 | 10 | 11 | 10.5 |  | 110 | 10 | 10.5
100 | 10 | 10 | 10.25 |  | 100 | 10 | 10.3333

## cart design
cart id | user id | status | item | quantity
user cart
cart id | user id | status
InProgress / Comfired / Cancel
cart Details
cart Detail id | cart id | item | quantity | Status
Add /Remove
user orders | user cart
order id | cart id

## Reported Issues
No. | Description | Status | Column1 | Column2 | date
1 | if pressing enter on sale invoice item system is not responding | Done | Delivery 1
2 | name field of the items visible should be adjusted | Done | Delivery 1
3 | edit quantity in the sale invoice | Done | Delivery 1
4 | add address in the pdf invoice printing for the customer. | Done | Delivery 1
5 | brand image is not showing. | Done | Delivery 1
6 | Item giving error while entring from the web | Done | Delivery 1
7 | Sale Invoice show be able to edit. | Done | Delivery 1
8 | Delete Sale Invoice. | Done | Delivery 1
9 | Edit / Detete Sale Invoice. | Done | Delivery 1
10 | Remove row from the sale Invoice while edit sale. | Done need to be tested | Delivery 2
11 | update Quantity while making invoice. | Done need to be tested | Delivery 2
12 | Search in the stock Report Screen. | Done need to be tested | Delivery 2
13 | Sale Report should show the name of the customer. | Done need to be tested | Delivery 2
14 | Sale Return should show Quantity instead of Invoice to return an item. | Done need to be tested | Delivery 2
15 | Add Quantity in the sale report |  | Delivery 3
16 | Edit / Delete Purcahse Invoice. | Done need to be tested | Delivery 4
17 | Enter id for the stock report | Done need to be tested | Delivery 4
18 | search item in and add filter options | Done need to be tested | Delivery 4
19 | Issues fixed in Return stock | Done need to be tested | Delivery 5
20 | Purchse report / Edit purchase should have name of the supplier | Done need to be tested | Delivery 5
21 | Fixed the Edit purchase issue with the DB update | Done need to be tested | Delivery 5 |  | 2022-02-02
20 | Issues fixed in Return stock (complete logic change) |  | Delivery 6 | only gui cahnges | 2022-02-08
show only online item having quantity greater than 0
timeout on huge purchase is causing issue